## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | INTRODUCTION TO PROJECT(AI based knowledge graph builder for interprise intelligence) | MUST HAVE | no dependency | Vishaka Shetty | 3- Completed
S1 | S1 | US-001 | Workflow Creation and Project Goal Document | MUST HAVE | lucid chart | Vishaka Shetty | 3- Completed
S2 | S2 | US-001 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | no dependency | Vishaka Shetty | 3- Completed
S2 | S2 | US-001 | Use Case Research and Dataset Preparation | SHOULD HAVE | Dataset | Vishaka Shetty | 3- Completed
S3 | S3 | US-001 | Using Python libraries preparing the data for processing | MUST HAVE | Python libraries | Vishaka Shetty | 3- Completed
S4 | S4 | US-001 | Selecting the best LLM Model | MUST HAVE | llm model | Vishaka Shetty | 3- Completed
S5 | S5 | US-001 | Extracted Entities and Relationships from Text using LLM store the results in neo4j | MUST HAVE | neo4j | Vishaka Shetty | 3- Completed
S6 | S6 | US-001 | Integrated the faiss and pinecone with system | SHOULD HAVE | faiss and pinecone | Vishaka Shetty | 3- Completed
S7 | S7 | US-001 | constructed the proper rag pipeline according to system requirements | SHOULD HAVE | cloud setup | Vishaka Shetty | 3- Completed
S8 | S8 | US-001 | Developed a simple interface to upload/query data | MUST HAVE | streamlit and fastapi | Vishaka Shetty | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | INTRODUCTION TO PROJECT(AI based knowledge graph builder for interprise intelligence) | 2026-02-02 | 2026-02-04 | Nikhil,Vishaka | other | 3-completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Workflow Creation and Project Goal Document | 2026-02-05 | 2026-02-08 | Nikhil,Vishaka | design | 3-completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 9/Feb//26 | 2026-02-15 | Nikhil,Vishaka | other | 3-completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Use Case Research and Dataset Preparation | 2026-02-16 | 2026-02-21 | Nikhil,Vishaka | other | 3-completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Using Python libraries preparing the data for processing | 2026-02-22 | 2026-03-27 | Nikhil,Vishaka | coding | 3-completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Selecting the best LLM Model | 2026-03-02 | 2026-03-07 | Vishaka,Nikhil | coding | 3-completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Extracted Entities and Relationships from Text using LLM store the results in neo4j | 2026-03-08 | 2026-03-11 | Vishaka,Nikhil | coding | 3-completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Integrated the faiss and pinecone with system | 2026-03-12 | 2026-03-17 | Vishaka,Nikhil | coding | 3-completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | constructed the proper rag pipeline according to system requirements | 2026-03-18 | 2026-03-20 | Vishaka,Nikhil | coding | 3-completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Developed a simple interface to upload/query data | 2026-03-21 | 2026-03-27 | Vishaka,Nikhil | design and coding | 3-completed | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Sprint 1 | 2026-02-02 | 2026-02-04 | Vishaka | Reviewing documentation regularly | Assuming we know everything | Participating in discussions and meetings | Took the help of mentor for resolving doubts
Sprint1 | Sprint 2 | 2026-02-16 | 2026-02-21 | Nikhil,vishaka | Find appropirate datset for the project | selecting random datasets | Finding best dataset Match the dataset with project requirement then selected it | Match the dataset with project requirements and then selected it
Sprint2 | Sprint 3 | 2026-03-02 | 2026-03-07 | Vishaka | testing different llm models | selecting any model without checking requirements parameters | store in results in neo4j and llm | tried out different llm models
Sprint2 | Sprint 4 | 2026-03-08 | 2026-03-17 | Vishaka | intergrating langchain and pincone with rag pipeline | Rushing through the entity extraction | store in results in neo4j and llm | created the rag pipeline while intergrating faiss and pipecone
Sprint2 | Day 9 | Confusion about llm model selection | Tried different models selected the one with best output
Sprint3 | Day 12 | Difficulty in intergrating neo4j with llm | Collaborated with Nikhil to resolve issues
Sprint4 | Day 16 | llm was following the orders properly and outputs were not clear | Optimised the llm and limited data to process it efficiently
Sprint5 | Day 23 | Challenges intergrating pincone and faiss | resolve it with help of mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-04 | Vishaka | Reviewing documentation regularly | Assuming we know everything | Participating in discussions and meetings | Took the help of mentor for resolving doubts
2 | Sprint 2 | 2026-02-16 | 2026-02-21 | Nikhil,vishaka | Find appropirate datset for the project | selecting random datasets | Finding best dataset Match the dataset with project requirement then selected it | Match the dataset with project requirements and then selected it
3 | Sprint 3 | 2026-03-02 | 2026-03-07 | Vishaka | testing different llm models | selecting any model without checking requirements parameters | store in results in neo4j and llm | tried out different llm models
4 | Sprint 4 | 2026-03-08 | 2026-03-17 | Vishaka | intergrating langchain and pincone with rag pipeline | Rushing through the entity extraction | store in results in neo4j and llm | created the rag pipeline while intergrating faiss and pipecone
5
6
7